## Hop Recommendations
ID | Recommendation Type | Evidence Level | Confidence Scope | Category | Target Table | SQL Objects Called | Description | Affected Jobs | Current Hops | Verified Hop Savings | Runtime Affected (sec) | Estimated Runtime Saved (sec) | Estimated Runtime Saved (min) | LLM Signals | LLM Redundancy Signals | LLM Performance Signals | LLM Logic Signals | Risk | Priority Score | Recommendation | Supporting Evidence | Edge Source Writes | Edge Target Reads | Implementation Decision | Execution Wave | Global RPT Count Impacted | Global Consumer Count | Global Runtime Affected (min) | Global Est Runtime Saved (min) | Blast Radius Score | Prerequisites
E-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE | CROSS_RPT_SHARED | E. MV Elimination Candidate | DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC | DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.main | WHAT: 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' is a pre-computed snapshot table (Materialized View) refreshed by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0'. CONSUMERS: 1 downstream job(s) in this RPT — EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23. OPPORTUNITY: Single-consumer MVs can be eliminated by inlining the MV's source query directly into the consumer, removing one pre-computation hop from the pipeline. | EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0 EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23 | 2 | 1 | 2829.3 | 991.8 | 16.53 | 0 | 0 | 0 | 0 | HIGH | 59 | SCOPE: LOCAL — execute within this RPT only. Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23. Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0'. Capture the SELECT query that populates 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' (the INSERT … SELECT or MERGE source). Step 3 [INLINE INTO CONSUMER] Open the SQL procedure called by consumer 'EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23'. Replace the direct table reference to 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' with the extracted query as a WITH (CTE) clause or subquery. Step 4 [VALIDATE] Run 3+ full pipeline cycles. Compare row counts and key metrics against the Step 1 baseline. Step 5 [DECOMMISSION] After parity is confirmed: • Remove Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0' from the Tidal schedule. • Drop table 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' from the database. • Remove all Tidal scheduler dependency edges pointing to this job. [JOB → SQL MAPPING] MV refresh job : EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0 [SQL: DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC] Consumer job : EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23 [SQL: PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA] |  |  |  | EXECUTE_GLOBAL_PROGRAM | GLOBAL_WAVE_1_PLUS | 3 | 1 | 47.16 | 30.62 | 3 | Row-count parity, key-metric parity, and 3-cycle runtime comparison Note: EXECUTE_GLOBAL_PROGRAM is set because the MV refresh job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0' appears as a Tidal scheduling dependency in 3 RPT pipeline(s) (RPT_CLAIMANT_DTL_R, RPT_CLAIM_DTL_R, RPT_DICS_CLAIMS_DETAIL_OAC_R). Even though only 1 job(s) consume the MV data, removing the refresh job from Tidal requires updating the dependency edges in ALL those RPT pipelines.
C-3 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SOURCE_SYSTEM_SPLIT | C. Source System Architectural Split (By Design) | FCT_GRP_PARTY_ADDRESS_R | PKG_GRP_LOAD_DIFW.main | 3 jobs load 'FCT_GRP_PARTY_ADDRESS_R' from distinct source systems (APS, CV, PACS), all calling 'PKG_GRP_LOAD_DIFW.main'. Jobs are intentionally separated for independent source-system hold management. | EDP_EDW_CV_SHINKA_LOAD_FCT_GRP_PARTY_ADDRESS_R EDP_EDW_GRP_APS_LOAD_FCT_GRP_PARTY_ADDRESS_R EDP_EDW_GRP_PACS_LOAD_FCT_GRP_PARTY_ADDRESS_R | 3 | 0 | 305.7 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 49 | Do not consolidate. Jobs are intentionally separated by source system (APS, CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies. |  |  |  | DEFER_OR_KEEP | DEFER | 1 | 0 | 0 | 0 | 0 | None — no change required
C-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SOURCE_SYSTEM_SPLIT | C. Source System Architectural Split (By Design) | DIM_GRP_CLAIM_DETAIL_R | PKG_GRP_LOAD_DIFW.main | 2 jobs load 'DIM_GRP_CLAIM_DETAIL_R' from distinct source systems (CV, PACS), all calling 'PKG_GRP_LOAD_DIFW.main'. Jobs are intentionally separated for independent source-system hold management. | EDP_EDW_CV_SHINKA_LOAD_DIM_GRP_CLAIM_DETAIL_R EDP_EDW_GRP_PACS_LOAD_DIM_GRP_CLAIM_DETAIL_R | 2 | 0 | 1291 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 48 | Do not consolidate. Jobs are intentionally separated by source system (CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies. |  |  |  | DEFER_OR_KEEP | DEFER | 1 | 0 | 0 | 0 | 0 | None — no change required
C-2 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SOURCE_SYSTEM_SPLIT | C. Source System Architectural Split (By Design) | DIM_GRP_PARTY_R | PKG_GRP_LOAD_DIFW.main | 2 jobs load 'DIM_GRP_PARTY_R' from distinct source systems (CV, PACS), all calling 'PKG_GRP_LOAD_DIFW.main'. Jobs are intentionally separated for independent source-system hold management. | EDP_EDW_CV_SHINKA_LOAD_DIM_GRP_PARTY_R EDP_EDW_GRP_PACS_LOAD_DIM_GRP_PARTY_R | 2 | 0 | 147.4 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 48 | Do not consolidate. Jobs are intentionally separated by source system (CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies. |  |  |  | DEFER_OR_KEEP | DEFER | 1 | 0 | 0 | 0 | 0 | None — no change required

## PLSQL Optimization
ID | Recommendation Type | Evidence Level | Confidence Scope | Category | Target Table | SQL Objects Called | Description | Affected Jobs | Current Hops | Verified Hop Savings | Runtime Affected (sec) | Estimated Runtime Saved (sec) | Estimated Runtime Saved (min) | LLM Signals | LLM Redundancy Signals | LLM Performance Signals | LLM Logic Signals | Risk | Priority Score | Recommendation | Supporting Evidence | Edge Source Writes | Edge Target Reads | Implementation Decision | Execution Wave | Global RPT Count Impacted | Global Consumer Count | Global Runtime Affected (min) | Global Est Runtime Saved (min) | Blast Radius Score | Prerequisites

## Summary
Category | # Recs | Verified Hop Savings | Est. Runtime Saved (min) | Unique Jobs Affected | Risk Level | Implementation Decision
HOP REDUCTION RECOMMENDATIONS (Structural / Verified — 4 total)
C. Source System Architectural Split (By Design) | 3 | 0 | 0 | 7 | LOW | DEFER_OR_KEEP
E. MV Elimination Candidate | 1 | 1 | 16.53 | 2 | HIGH | EXECUTE_GLOBAL_PROGRAM
Hop Reduction Subtotal | 4 | 1 | 16.53 | 9
F. OPTIMIZATION FINDINGS (Require SQL / Code Review — 0 total)
Optimization Subtotal | 0 | 0 | 0 | 0
GRAND TOTAL | 4 | 1 | 16.53 | 9

## Global Decisions
ID | Category | Target Table | Impacted RPTs | Impacted Jobs | Global Consumer Count | Global Est Runtime Saved (min) | Blast Radius | Execution Wave | Recommendation | Implementation Steps
E-1 | E. MV Elimination Candidate | DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC | RPT_CLAIMANT_DTL_R, RPT_CLAIM_DTL_R, RPT_DICS_CLAIMS_DETAIL_OAC_R | MV Refresh Job (writes 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC'): EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0 SQL: DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC Consumer Jobs — 1 unique job(s), 3 total job-instances across 3 RPT(s). (Updating the SQL procedures below removes the MV dependency across all listed RPTs) RPT_CLAIMANT_DTL_R (1 job(s)): • EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23 SQL: PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA RPT_CLAIM_DTL_R (1 job(s)): • EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23 SQL: PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA RPT_DICS_CLAIMS_DETAIL_OAC_R (1 job(s)): • EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23 SQL: PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA | 1 | 30.62 | 3 | GLOBAL_WAVE_1_PLUS | SCOPE: LOCAL — execute within this RPT only. Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23. Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0'. Capture the SELECT query that populates 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' (the INSERT … SELECT or MERGE source). Step 3 [INLINE INTO CONSUMER] Open the SQL procedure called by consumer 'EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23'. Replace the direct table reference to 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' with the extracted query as a WITH (CTE) clause or subquery. Step 4 [VALIDATE] Run 3+ full pipeline cycles. Compare row counts and key metrics against the Step 1 baseline. Step 5 [DECOMMISSION] After parity is confirmed: • Remove Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0' from the Tidal schedule. • Drop table 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' from the database. • Remove all Tidal scheduler dependency edges pointing to this job. [JOB → SQL MAPPING] MV refresh job : EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0 [SQL: DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC] Consumer job : EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23 [SQL: PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA] | STEP 1 — ESTABLISH BASELINE (all 3 RPTs) Before any code change, capture these metrics for EVERY RPT pipeline listed: • Row counts in each consumer job's target table • End-to-end cycle-time per RPT (wall clock) • SLA breach count over the last 5 runs per RPT RPTs to baseline: RPT_CLAIMANT_DTL_R, RPT_CLAIM_DTL_R, RPT_DICS_CLAIMS_DETAIL_OAC_R Store results in a shared comparison spreadsheet for parity sign-off. STEP 2 — EXTRACT MV SOURCE DEFINITION (one-time, reused by all consumers) Open SQL procedure: DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC Find the INSERT … SELECT (or MERGE) that populates 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC'. Copy the core SELECT query and save it as a shared CTE template: WITH DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC AS ( <paste extracted SELECT here> ) This single CTE definition will be added to EVERY consumer job below. STEP 3 — WAVE 1 CODE CHANGES (1 unique SQL procedure(s) to change) Job : EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23 SQL : PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA Impacts: 3 RPT(s): RPT_CLAIMANT_DTL_R, RPT_CLAIM_DTL_R, RPT_DICS_CLAIMS_DETAIL_OAC_R Changes required: a) Open PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA and add the CTE from Step 2 at the top. b) Replace every FROM / JOIN reference to 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' with the CTE name. c) This ONE SQL change resolves all 3 RPT pipeline(s) above. d) After parity (Step 4), remove the Tidal dependency edge on 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0' in each of the 3 affected RPT Tidal schedule(s). STEP 4 — WAVE 1 VALIDATION (all 3 RPTs) Deploy Wave changes and run 3+ full pipeline cycles for ALL affected RPTs. Confirm across every RPT: • Row counts match the Step 1 baseline (±0). • Key metrics (claim totals, payment amounts) are identical. Do NOT proceed to the next wave until ALL RPTs have signed off on parity. STEP 5 — TIDAL SCHEDULER CLEANUP (repeat for each of the 3 RPT schedules) Once ALL consumer jobs have passed parity in PRODUCTION: For EACH RPT in [RPT_CLAIMANT_DTL_R, RPT_CLAIM_DTL_R, RPT_DICS_CLAIMS_DETAIL_OAC_R]: • Remove Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0' from that RPT's Tidal schedule. • Delete ALL inbound Tidal dependency edges pointing TO 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0'. • Delete ALL outbound Tidal dependency edges pointing FROM 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0'. STEP 6 — DATABASE CLEANUP (global, one-time) • EXEC sp_rename 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC', 'DEPRECATED_DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' — 30-day safety hold. • After 30 days with no incidents across ALL 3 RPTs: DROP TABLE DEPRECATED_DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC • Remove any SQL VIEWs, synonyms, or grants referencing this table.

## RPT Rollout Plan
Execution Wave | ID | Category | Target Table | Scope | Risk | Priority Score | # Affected Jobs | Affected Jobs (List) | Prerequisites
Global Wave — Cross-RPT Program (1 items)
Global Wave — Cross-RPT Program | E-1 | E. MV Elimination Candidate | DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC | GLOBAL | HIGH | 59 | 2 | EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0 EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23 | Row-count parity, key-metric parity, and 3-cycle runtime comparison Note: EXECUTE_GLOBAL_PROGRAM is set because the MV refresh job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0' appears as a Tidal scheduling dependency in 3 RPT pipeline(s) (RPT_CLAIMANT_DTL_R, RPT_CLAIM_DTL_R, RPT_DICS_CLAIMS_DETAIL_OAC_R). Even though only 1 job(s) consume the MV data, removing the refresh job from Tidal requires updating the dependency edges in ALL those RPT pipelines.

## Action Items
Rank | ID | Category | Target Table | Risk | Scope | Priority Score | What To Do | SQL Objects | Est. Saved (min)
1 | E-1 | E. MV Elimination Candidate | DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC | HIGH | GLOBAL | 59 | Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23. Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0'. Capture the SELECT query that populates 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' (the INSERT … SELECT or MERGE source). Step 3 [INLINE INTO CONSUMER] Open the SQL procedure called by consumer 'EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23'. Replace the direct table reference to 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' with the extracted query as a WITH (CTE) clause or subquery. Step 4 [VALIDATE] Run 3+ full pipeline cycles. Compare row counts and key metrics against the Step 1 baseline. Step 5 [DECOMMISSION] After parity is confirmed: [JOB → SQL MAPPING] | DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.main | 16.53

## Graph Overview
RPT Table | RPT_CLAIMANT_DTL_R
Total Nodes | 9
Total Edges | 9
Max Depth | 1
Node Category Breakdown
Category | Count
DIM | 4
FCT | 3
RPT | 1
MV | 1
Depth Breakdown
Depth | Node Count | Categories
0 | 1 | RPT:1
1 | 8 | DIM:4, FCT:3, MV:1

## Savings Simulation
Parameter | Value | What this means
RPT Table | RPT_CLAIMANT_DTL_R | The report pipeline being analysed
Original node count | 9 | Total Tidal jobs in the dependency graph (root + all upstream dependencies)
Original max depth | 1 | Longest chain of dependent jobs (critical path). Determines minimum pipeline latency.
Jobs removed in simulation (top 10 recs) | 0 | Jobs conceptually eliminated based on the top 10 recommendations (parallelise chain, fold pass-through, consolidate loaders, etc.)
New node count (after simulation) | 9 | Remaining jobs if all top 10 recommendations are implemented
New max depth (after simulation) | 1 | Estimated new critical-path length after removals. Only jobs still connected to root are counted.
Depth reduction | 0 | How many sequential hops are removed from the critical path (pipeline latency improvement)
Node reduction | 0 | How many jobs are eliminated entirely (maintenance and scheduling overhead reduction)
Est. runtime saved — top 10 recs (min) | 16.53 | Sum of estimated pipeline time saved based on avg_runtime data for affected jobs
Verified hop savings — top 10 recs | 1 | Total hops with hard lineage/graph evidence that they can be removed (excludes LLM-only estimates)
Jobs removed in simulation (first 15):

## Job_Optimization_Plan
Job | Script / SQL Object | Step # | Category | Target Table | Risk | Verified Hop Savings | Action Summary
EDP_EDW_CV_SHINKA_LOAD_DIM_GRP_CLAIM_DETAIL_R | PKG_GRP_LOAD_DIFW.main | 1 | C. Source System Architectural Split (By Design) | DIM_GRP_CLAIM_DETAIL_R | LOW | 0 | Do not consolidate. Jobs are intentionally separated by source system (CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies.
EDP_EDW_CV_SHINKA_LOAD_DIM_GRP_PARTY_R | PKG_GRP_LOAD_DIFW.main | 1 | C. Source System Architectural Split (By Design) | DIM_GRP_PARTY_R | LOW | 0 | Do not consolidate. Jobs are intentionally separated by source system (CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies.
EDP_EDW_CV_SHINKA_LOAD_FCT_GRP_PARTY_ADDRESS_R | PKG_GRP_LOAD_DIFW.main | 1 | C. Source System Architectural Split (By Design) | FCT_GRP_PARTY_ADDRESS_R | LOW | 0 | Do not consolidate. Jobs are intentionally separated by source system (APS, CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies.
EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0 | DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC, PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.PRC_DEL_EXT_DATA, PKG_GRP_LOAD_RPT_CLAIMANT_DTL_R_INC.main | 1 | E. MV Elimination Candidate | DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC | HIGH | 1 | SCOPE: LOCAL — execute within this RPT only. ¦ Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_LOAD_RPT_CLAIMANT_DTL_R-23. ¦ Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_DETAIL_R_MV_SSL-0'. Capture the SELECT query that populates 'DIM_GRP_CLAIM_DETAIL_R_MV_SSL_INC' (the INSERT … SELECT or