## Hop Recommendations
ID | Recommendation Type | Evidence Level | Confidence Scope | Category | Target Table | SQL Objects Called | Description | Affected Jobs | Current Hops | Verified Hop Savings | Runtime Affected (sec) | Estimated Runtime Saved (sec) | Estimated Runtime Saved (min) | LLM Signals | LLM Redundancy Signals | LLM Performance Signals | LLM Logic Signals | Risk | Priority Score | Recommendation | Supporting Evidence | Edge Source Writes | Edge Target Reads | Implementation Decision | Execution Wave | Global RPT Count Impacted | Global Consumer Count | Global Runtime Affected (min) | Global Est Runtime Saved (min) | Blast Radius Score | Prerequisites
O-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS | 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' is an Oracle Global Temporary Table (GTT) — the '_GTT' suffix is the correct Oracle naming convention, so NO rename is needed. Script analysis confirms it is created and consumed within the same stored procedure (intra-procedure staging). GTTs represent a physical staging hop that may be eliminatable. | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 62 | NAMING: No rename needed — '_GTT' is the correct Oracle convention. HOP REDUCTION: 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' stages data between steps within the same procedure. Evaluate replacing with a WITH clause (CTE): (1) If the result is read MORE than once inside the procedure → keep the GTT (Oracle may re-execute a CTE each time it is referenced). (2) If the result is read EXACTLY ONCE → rewrite as a CTE to eliminate the physical write/read cycle. (3) Validate row counts and key metrics before and after the change. |  |  |  | EXECUTE_GLOBAL_PROGRAM | GLOBAL_WAVE_1_PLUS | 5 | 0 | 49.76 | 0 | 5 | Verify the GTT result set is referenced only once; if referenced multiple times, keep the GTT (CTE re-evaluation risk in Oracle).
C-4 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SAME_PKG_VARIANT | C. Near-Duplicate Procedures | rpt_claim_sum_r | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 2 jobs load 'rpt_claim_sum_r' with >=85% identical target column sets. SQL objects called: ['PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA', 'PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS', 'PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main']. | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 61 | Jobs call different variants of the same base package. Evaluate if variants can be unified with a single parameterized package entry point. [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS |  |  |  | EXECUTE_LOCALLY | WAVE_1 | 1 | 1 | 5.38 | 0 | 2 | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
E-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE | CROSS_RPT_SHARED | E. MV Elimination Candidate | DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL | DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC | WHAT: 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' is a pre-computed snapshot table (Materialized View) refreshed by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2'. CONSUMERS: 1 downstream job(s) in this RPT — EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3. OPPORTUNITY: Single-consumer MVs can be eliminated by inlining the MV's source query directly into the consumer, removing one pre-computation hop from the pipeline. COMPLEXITY: HIGH — MV reads from 5 source tables. Full SQL analysis required before inlining; logic may be too complex to safely embed as a single CTE. Engage the SQL author. | EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2 EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 | 2 | 1 | 1481.7 | 114.8 | 1.91 | 0 | 0 | 0 | 0 | HIGH | 55 | SCOPE: LOCAL — execute within this RPT only. Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3. Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2'. Capture the SELECT query that populates 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' (the INSERT … SELECT or MERGE source). Step 3 [INLINE INTO CONSUMER] Open the SQL procedure called by consumer 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Replace the direct table reference to 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' with the extracted query as a WITH (CTE) clause or subquery. Step 4 [VALIDATE] Run 3+ full pipeline cycles. Compare row counts and key metrics against the Step 1 baseline. Step 5 [DECOMMISSION] After parity is confirmed: • Remove Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2' from the Tidal schedule. • Drop table 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' from the database. • Remove all Tidal scheduler dependency edges pointing to this job. [JOB → SQL MAPPING] MV refresh job : EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2 [SQL: DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL] Consumer job : EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 [SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC] |  |  |  | EXECUTE_GLOBAL_PROGRAM | GLOBAL_WAVE_1_PLUS | 6 | 1 | 24.7 | 1.91 | 6 | Row-count parity, key-metric parity, and 3-cycle runtime comparison Note: EXECUTE_GLOBAL_PROGRAM is set because the MV refresh job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2' appears as a Tidal scheduling dependency in 6 RPT pipeline(s) (RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST). Even though only 1 job(s) consume the MV data, removing the refresh job from Tidal requires updating the dependency edges in ALL those RPT pipelines.
E-2 | HOP_REDUCTION | GRAPH_OR_LINEAGE | CROSS_RPT_SHARED | E. MV Elimination Candidate | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.main | WHAT: 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' is a pre-computed snapshot table (Materialized View) refreshed by Tidal job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. CONSUMERS: 1 downstream job(s) in this RPT — EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18. OPPORTUNITY: Single-consumer MVs can be eliminated by inlining the MV's source query directly into the consumer, removing one pre-computation hop from the pipeline. COMPLEXITY: MEDIUM — MV reads from 3 source tables. Review JOIN logic carefully before inlining. | EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 | 2 | 1 | 1694.7 | 327.8 | 5.46 | 0 | 0 | 0 | 0 | HIGH | 54 | SCOPE: LOCAL — execute within this RPT only. Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18. Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Capture the SELECT query that populates 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' (the INSERT … SELECT or MERGE source). Step 3 [INLINE INTO CONSUMER] Open the SQL procedure called by consumer 'EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18'. Replace the direct table reference to 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' with the extracted query as a WITH (CTE) clause or subquery. Step 4 [VALIDATE] Run 3+ full pipeline cycles. Compare row counts and key metrics against the Step 1 baseline. Step 5 [DECOMMISSION] After parity is confirmed: • Remove Tidal job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' from the Tidal schedule. • Drop table 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' from the database. • Remove all Tidal scheduler dependency edges pointing to this job. [JOB → SQL MAPPING] MV refresh job : EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 [SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC] Consumer job : EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 [SQL: PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA] |  |  |  | EXECUTE_GLOBAL_PROGRAM | GLOBAL_WAVE_1_PLUS | 6 | 1 | 28.25 | 22.78 | 6 | Row-count parity, key-metric parity, and 3-cycle runtime comparison Note: EXECUTE_GLOBAL_PROGRAM is set because the MV refresh job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' appears as a Tidal scheduling dependency in 6 RPT pipeline(s) (RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST). Even though only 1 job(s) consume the MV data, removing the refresh job from Tidal requires updating the dependency edges in ALL those RPT pipelines.
M-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | M. Orchestration Edge Without Data Handoff (MV->MV) | FCT_GRP_CLAIM_NOTE_R_MV_SSL | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC FCT_GRP_CLAIM_NOTE_R_MV_SSL | Dependency edge 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1' -> 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' has no table handoff. Upstream writes ['FCT_GRP_CLAIM_NOTE_R_MV_SSL'] but downstream reads ['DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL', 'DIM_GRP_SYSUSESO_R', 'FCT_GRP_CLAIM_NOTE_R']. Intersection is empty. Successors of source: 2; parents of target: 2. | EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1 EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 | 1 | 1 | 2717.7 | 1350.8 | 22.51 | 0 | 0 | 0 | 0 | MEDIUM | 52 | Validate edge-level dependency cleanup for 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1' -> 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Checklist: (1) confirm 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' SQL does not reference ['FCT_GRP_CLAIM_NOTE_R_MV_SSL'], (2) verify no hidden side-effects/temp-table dependencies, (3) remove or relax this scheduler edge in Tidal, (4) run parity + cycle-time comparison for 3+ runs. |  | FCT_GRP_CLAIM_NOTE_R_MV_SSL | DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL DIM_GRP_SYSUSESO_R FCT_GRP_CLAIM_NOTE_R | EXECUTE_LOCALLY | WAVE_2 | 1 | 1 | 45.29 | 22.51 | 2 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
A-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE | DIFF_SQL_OBJECTS | A. Redundant Multi-Source Load | RPT_CLAIM_DTL_R | PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS | Table 'RPT_CLAIM_DTL_R' loaded by 2 jobs: ['EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19', 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS']. SQL: ['PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS'] | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEDIUM | 47 | Investigate if loads can be consolidated. [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19, EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS |  |  |  | EXECUTE_LOCALLY | WAVE_2 | 1 | 1 | 51.05 | 0 | 2 | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
A-2 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SAME_PKG_VARIANT | A. Redundant Multi-Source Load | rpt_claim_sum_r | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | Table 'rpt_claim_sum_r' loaded by 2 jobs: ['EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22', 'EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS']. SQL: ['PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA', 'PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS', 'PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main'] | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEDIUM | 47 | Investigate if loads can be consolidated. [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS |  |  |  | EXECUTE_LOCALLY | WAVE_2 | 1 | 1 | 5.38 | 0 | 2 | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
E-3 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | E. Dead MV — Zero Consumers (Decommission Candidate) | FCT_GRP_CLAIM_NOTE_R_MV_SSL | FCT_GRP_CLAIM_NOTE_R_MV_SSL | MV 'FCT_GRP_CLAIM_NOTE_R_MV_SSL' is refreshed by job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1' but has NO consumers in the pipeline: zero readers found in column-level lineage AND zero references found in script summaries. The pipeline bypasses this MV and reads from the underlying base table directly. This is a scheduler-topology issue: the refresh job runs on schedule, consuming compute resources, but the output is never used. Confirmed across all RPT graphs: 0 consumers globally. | EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1 | 1 | 1 | 1350.8 | 1350.8 | 22.51 | 0 | 0 | 0 | 0 | MEDIUM | 47 | DECOMMISSION CANDIDATE — Action required: (1) Confirm 'FCT_GRP_CLAIM_NOTE_R_MV_SSL' has no consumers by searching all SQL packages and procedures for any SELECT/JOIN referencing 'FCT_GRP_CLAIM_NOTE_R_MV_SSL'. (2) Cross-verify with the script LLM summaries: the table does NOT appear in any summary's INPUT_DEPENDENCIES — supporting the dead-write assessment. (3) If confirmed zero usage, remove the refresh job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1' from the Tidal schedule and drop the MV definition. (4) Verify that removing 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1' does not break any downstream Tidal dependencies (check children jobs: ['EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18', 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3']). (5) If children jobs depend on 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1' purely for ordering, replace with a direct dependency on the upstream base-table load job instead. |  |  |  | EXECUTE_LOCALLY | WAVE_2 | 1 | 0 | 22.51 | 22.51 | 1 | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
G-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | G. Duplicate Column-Lineage Paths | rpt_claim_sum_r | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 1 columns flow lt_var_upd_tbl_amt_typ, lt_var_upd_tbl_reserveamt_typ, lt_var_upd_tbl_typ3 -> rpt_claim_sum_r via 2 different jobs (same path). | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEDIUM | 43 | Consolidate column writes - only 1 job needs to load 1 columns from lt_var_upd_tbl_amt_typ, lt_var_upd_tbl_reserveamt_typ, lt_var_upd_tbl_typ3 -> rpt_claim_sum_r. |  |  |  | EXECUTE_LOCALLY | WAVE_2 | 1 | 1 | 5.38 | 0 | 2 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
C-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SOURCE_SYSTEM_SPLIT | C. Source System Architectural Split (By Design) | DIM_GRP_CLAIM_DETAIL_R | PKG_GRP_LOAD_DIFW.main | 2 jobs load 'DIM_GRP_CLAIM_DETAIL_R' from distinct source systems (CV, PACS), all calling 'PKG_GRP_LOAD_DIFW.main'. Jobs are intentionally separated for independent source-system hold management. | EDP_EDW_CV_SHINKA_LOAD_DIM_GRP_CLAIM_DETAIL_R EDP_EDW_GRP_PACS_LOAD_DIM_GRP_CLAIM_DETAIL_R | 2 | 0 | 1291 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 38 | Do not consolidate. Jobs are intentionally separated by source system (CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies. |  |  |  | DEFER_OR_KEEP | DEFER | 1 | 0 | 0 | 0 | 0 | None — no change required
C-2 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SOURCE_SYSTEM_SPLIT | C. Source System Architectural Split (By Design) | DIM_GRP_CLAIM_DIR_R | PKG_GRP_LOAD_DIFW.main | 2 jobs load 'DIM_GRP_CLAIM_DIR_R' from distinct source systems (CV, PACS), all calling 'PKG_GRP_LOAD_DIFW.main'. Jobs are intentionally separated for independent source-system hold management. | EDP_EDW_CV_SHINKA_LOAD_DIM_GRP_CLAIM_DIR_R EDP_EDW_GRP_PACS_LOAD_DIM_GRP_CLAIM_DIR_R | 2 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 38 | Do not consolidate. Jobs are intentionally separated by source system (CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies. |  |  |  | DEFER_OR_KEEP | DEFER | 1 | 0 | 0 | 0 | 0 | None — no change required
C-3 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SOURCE_SYSTEM_SPLIT | C. Source System Architectural Split (By Design) | FCT_GRP_POLICY_R | PKG_GRP_LOAD_DIFW.main | 2 jobs load 'FCT_GRP_POLICY_R' from distinct source systems (PACS, SHINKA), all calling 'PKG_GRP_LOAD_DIFW.main'. Jobs are intentionally separated for independent source-system hold management. | EDP_EDW_EIS_SHINKA_LOAD_FCT_GRP_POLICY_R EDP_EDW_GRP_PACS_LOAD_FCT_GRP_POLICY_R | 2 | 0 | 64.8 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 38 | Do not consolidate. Jobs are intentionally separated by source system (PACS, SHINKA) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies. |  |  |  | DEFER_OR_KEEP | DEFER | 1 | 0 | 0 | 0 | 0 | None — no change required
N-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | N. Circular Update Chain (Post-Load Self-Reference) | RPT_CLAIM_DTL_R | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS | Job 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' is a full-load job for 'RPT_CLAIM_DTL_R', but it also reads ['RPT_FCT_RPT_CLAIM_SUMMARY_R'] — table(s) that are DOWNSTREAM of 'RPT_CLAIM_DTL_R' (i.e., they are derived FROM 'RPT_CLAIM_DTL_R' in a previous pipeline cycle). This creates a lagged-cycle circular dependency: the current-run load uses last-cycle aggregated/derived data to fill in indicator or decision columns, meaning the output of 'RPT_CLAIM_DTL_R' in this cycle will differ from what it would be if fresh data were used. Note: 'RPT_CLAIM_DTL_R' gets updated using RPT_FCT_RPT_CLAIM_SUMMARY_R, which is itself derived from 'RPT_CLAIM_DTL_R' — this is a circular feedback loop across pipeline cycles. | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HIGH | 28 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_CLAIM_DTL_R' are derived from ['RPT_FCT_RPT_CLAIM_SUMMARY_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' by joining to the underlying DIM/FCT tables that feed RPT_FCT_RPT_CLAIM_SUMMARY_R, rather than reading the pre-aggregated summary. (3) This eliminates the cross-cycle lag — the indicator columns will reflect the CURRENT cycle's source data instead of the previous cycle's summary. (4) Validate: run 3 consecutive daily cycles comparing row counts and indicator column distributions before/after the change. Risk: HIGH — the folded logic must produce equivalent results to avoid silent data drift in downstream reports. |  |  |  | EXECUTE_LOCALLY | WAVE_3 | 1 | 0 | 49.76 | 0 | 1 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
N-2 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | N. Circular Update Chain (Post-Load Self-Reference) | RPT_FCT_RPT_CLAIM_SUMMARY_R | PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.main | Job 'EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24' is a full-load job for 'RPT_FCT_RPT_CLAIM_SUMMARY_R', but it also reads ['RPT_CLAIM_DTL_R'] — table(s) that are DOWNSTREAM of 'RPT_FCT_RPT_CLAIM_SUMMARY_R' (i.e., they are derived FROM 'RPT_FCT_RPT_CLAIM_SUMMARY_R' in a previous pipeline cycle). This creates a lagged-cycle circular dependency: the current-run load uses last-cycle aggregated/derived data to fill in indicator or decision columns, meaning the output of 'RPT_FCT_RPT_CLAIM_SUMMARY_R' in this cycle will differ from what it would be if fresh data were used. Note: 'RPT_FCT_RPT_CLAIM_SUMMARY_R' gets updated using RPT_CLAIM_DTL_R, which is itself derived from 'RPT_FCT_RPT_CLAIM_SUMMARY_R' — this is a circular feedback loop across pipeline cycles. | EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HIGH | 28 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_FCT_RPT_CLAIM_SUMMARY_R' are derived from ['RPT_CLAIM_DTL_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24' by joining to the underlying DIM/FCT tables that feed RPT_CLAIM_DTL_R, rather than reading the pre-aggregated summary. (3) This eliminates the cross-cycle lag — the indicator columns will reflect the CURRENT cycle's source data instead of the previous cycle's summary. (4) Validate: run 3 consecutive daily cycles comparing row counts and indicator column distributions before/after the change. Risk: HIGH — the folded logic must produce equivalent results to avoid silent data drift in downstream reports. |  |  |  | EXECUTE_LOCALLY | WAVE_3 | 1 | 0 | 11.18 | 0 | 1 | Row-count parity and cycle-time comparison for 3+ runs within this RPT

## PLSQL Optimization
ID | Recommendation Type | Evidence Level | Confidence Scope | Category | Target Table | SQL Objects Called | Description | Affected Jobs | Current Hops | Verified Hop Savings | Runtime Affected (sec) | Estimated Runtime Saved (sec) | Estimated Runtime Saved (min) | LLM Signals | LLM Redundancy Signals | LLM Performance Signals | LLM Logic Signals | Risk | Priority Score | Recommendation | Supporting Evidence | Edge Source Writes | Edge Target Reads | Implementation Decision | Execution Wave | Global RPT Count Impacted | Global Consumer Count | Global Runtime Affected (min) | Global Est Runtime Saved (min) | Blast Radius Score | Prerequisites

## Summary
Category | # Recs | Verified Hop Savings | Est. Runtime Saved (min) | Unique Jobs Affected | Risk Level | Implementation Decision
HOP REDUCTION RECOMMENDATIONS (Structural / Verified — 14 total)
A. Redundant Multi-Source Load | 2 | 2 | 0 | 4 | MEDIUM | EXECUTE_LOCALLY
C. Near-Duplicate Procedures | 1 | 1 | 0 | 2 | LOW | EXECUTE_LOCALLY
C. Source System Architectural Split (By Design) | 3 | 0 | 0 | 6 | LOW | DEFER_OR_KEEP
E. Dead MV — Zero Consumers (Decommission Candidate) | 1 | 1 | 22.51 | 1 | MEDIUM | EXECUTE_LOCALLY
E. MV Elimination Candidate | 2 | 2 | 7.37 | 3 | HIGH | EXECUTE_GLOBAL_PROGRAM
G. Duplicate Column-Lineage Paths | 1 | 1 | 0 | 2 | MEDIUM | EXECUTE_LOCALLY
M. Orchestration Edge Without Data Handoff (MV->MV) | 1 | 1 | 22.51 | 2 | MEDIUM | EXECUTE_LOCALLY
N. Circular Update Chain (Post-Load Self-Reference) | 2 | 2 | 0 | 2 | HIGH | EXECUTE_LOCALLY
O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | 1 | 1 | 0 | 1 | LOW | EXECUTE_GLOBAL_PROGRAM
Hop Reduction Subtotal | 14 | 11 | 52.39 | 15
F. OPTIMIZATION FINDINGS (Require SQL / Code Review — 0 total)
Optimization Subtotal | 0 | 0 | 0 | 0
GRAND TOTAL | 14 | 11 | 52.39 | 15

## Global Decisions
ID | Category | Target Table | Impacted RPTs | Impacted Jobs | Global Consumer Count | Global Est Runtime Saved (min) | Blast Radius | Execution Wave | Recommendation | Implementation Steps
O-1 | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | RPT_CLAIM_DTL_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST | MV Refresh Job (writes 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT'): EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 SQL: PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS Consumer Jobs — 0 job(s): | 0 | 0 | 5 | GLOBAL_WAVE_1_PLUS | NAMING: No rename needed — '_GTT' is the correct Oracle convention. HOP REDUCTION: 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' stages data between steps within the same procedure. Evaluate replacing with a WITH clause (CTE): (1) If the result is read MORE than once inside the procedure → keep the GTT (Oracle may re-execute a CTE each time it is referenced). (2) If the result is read EXACTLY ONCE → rewrite as a CTE to eliminate the physical write/read cycle. (3) Validate row counts and key metrics before and after the change. | STEP 1 — ESTABLISH BASELINE (all 5 RPTs) Before any code change, capture these metrics for EVERY RPT pipeline listed: • Row counts in each consumer job's target table • End-to-end cycle-time per RPT (wall clock) • SLA breach count over the last 5 runs per RPT RPTs to baseline: RPT_CLAIM_DTL_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST Store results in a shared comparison spreadsheet for parity sign-off. STEP 2 — EXTRACT MV SOURCE DEFINITION (one-time, reused by all consumers) Open SQL procedure: PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS Find the INSERT … SELECT (or MERGE) that populates 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT'. Copy the core SELECT query and save it as a shared CTE template: WITH RPT_CLAIM_DTL_R_CLAIMDEC_GTT AS ( <paste extracted SELECT here> ) This single CTE definition will be added to EVERY consumer job below. STEP 3 — TIDAL SCHEDULER CLEANUP (repeat for each of the 5 RPT schedules) Once ALL consumer jobs have passed parity in PRODUCTION: For EACH RPT in [RPT_CLAIM_DTL_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST]: • Remove Tidal job 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' from that RPT's Tidal schedule. • Delete ALL inbound Tidal dependency edges pointing TO 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19'. • Delete ALL outbound Tidal dependency edges pointing FROM 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19'. STEP 4 — DATABASE CLEANUP (global, one-time) • EXEC sp_rename 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT', 'DEPRECATED_RPT_CLAIM_DTL_R_CLAIMDEC_GTT' — 30-day safety hold. • After 30 days with no incidents across ALL 5 RPTs: DROP TABLE DEPRECATED_RPT_CLAIM_DTL_R_CLAIMDEC_GTT • Remove any SQL VIEWs, synonyms, or grants referencing this table.
E-1 | E. MV Elimination Candidate | DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL | RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST | MV Refresh Job (writes 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL'): EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2 SQL: DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL Consumer Jobs — 1 unique job(s), 6 total job-instances across 6 RPT(s). (Updating the SQL procedures below removes the MV dependency across all listed RPTs) RPT_CLAIM_DTL_R (1 job(s)): • EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC RPT_CLAIM_NOTE_R (1 job(s)): • EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC RPT_CLAIM_SUM_R (1 job(s)): • EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC RPT_DICS_CLAIMS_DETAIL_OAC_R (1 job(s)): • EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC RPT_FCT_RPT_CLAIM_SUMMARY_R (1 job(s)): • EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST (1 job(s)): • EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC | 1 | 1.91 | 6 | GLOBAL_WAVE_1_PLUS | SCOPE: LOCAL — execute within this RPT only. Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3. Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2'. Capture the SELECT query that populates 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' (the INSERT … SELECT or MERGE source). Step 3 [INLINE INTO CONSUMER] Open the SQL procedure called by consumer 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Replace the direct table reference to 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' with the extracted query as a WITH (CTE) clause or subquery. Step 4 [VALIDATE] Run 3+ full pipeline cycles. Compare row counts and key metrics against the Step 1 baseline. Step 5 [DECOMMISSION] After parity is confirmed: • Remove Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2' from the Tidal schedule. • Drop table 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' from the database. • Remove all Tidal scheduler dependency edges pointing to this job. [JOB → SQL MAPPING] MV refresh job : EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2 [SQL: DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL] Consumer job : EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 [SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC] | STEP 1 — ESTABLISH BASELINE (all 6 RPTs) Before any code change, capture these metrics for EVERY RPT pipeline listed: • Row counts in each consumer job's target table • End-to-end cycle-time per RPT (wall clock) • SLA breach count over the last 5 runs per RPT RPTs to baseline: RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST Store results in a shared comparison spreadsheet for parity sign-off. STEP 2 — EXTRACT MV SOURCE DEFINITION (one-time, reused by all consumers) Open SQL procedure: DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL Find the INSERT … SELECT (or MERGE) that populates 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL'. Copy the core SELECT query and save it as a shared CTE template: WITH DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL AS ( <paste extracted SELECT here> ) This single CTE definition will be added to EVERY consumer job below. STEP 3 — WAVE 1 CODE CHANGES (1 unique SQL procedure(s) to change) Job : EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 SQL : FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC Impacts: 6 RPT(s): RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST Changes required: a) Open FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC and add the CTE from Step 2 at the top. b) Replace every FROM / JOIN reference to 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' with the CTE name. c) This ONE SQL change resolves all 6 RPT pipeline(s) above. d) After parity (Step 4), remove the Tidal dependency edge on 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2' in each of the 6 affected RPT Tidal schedule(s). STEP 4 — WAVE 1 VALIDATION (all 6 RPTs) Deploy Wave changes and run 3+ full pipeline cycles for ALL affected RPTs. Confirm across every RPT: • Row counts match the Step 1 baseline (±0). • Key metrics (claim totals, payment amounts) are identical. Do NOT proceed to the next wave until ALL RPTs have signed off on parity. STEP 5 — TIDAL SCHEDULER CLEANUP (repeat for each of the 6 RPT schedules) Once ALL consumer jobs have passed parity in PRODUCTION: For EACH RPT in [RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST]: • Remove Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2' from that RPT's Tidal schedule. • Delete ALL inbound Tidal dependency edges pointing TO 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2'. • Delete ALL outbound Tidal dependency edges pointing FROM 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2'. STEP 6 — DATABASE CLEANUP (global, one-time) • EXEC sp_rename 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL', 'DEPRECATED_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' — 30-day safety hold. • After 30 days with no incidents across ALL 6 RPTs: DROP TABLE DEPRECATED_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL • Remove any SQL VIEWs, synonyms, or grants referencing this table.
E-2 | E. MV Elimination Candidate | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC | RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST | MV Refresh Job (writes 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC'): EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC Consumer Jobs — 1 unique job(s), 6 total job-instances across 6 RPT(s). (Updating the SQL procedures below removes the MV dependency across all listed RPTs) RPT_CLAIM_DTL_R (1 job(s)): • EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 SQL: PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA RPT_CLAIM_NOTE_R (1 job(s)): • EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 SQL: PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA RPT_CLAIM_SUM_R (1 job(s)): • EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 SQL: PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA RPT_DICS_CLAIMS_DETAIL_OAC_R (1 job(s)): • EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 SQL: PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA RPT_FCT_RPT_CLAIM_SUMMARY_R (1 job(s)): • EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 SQL: PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST (1 job(s)): • EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 SQL: PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA | 1 | 22.78 | 6 | GLOBAL_WAVE_1_PLUS | SCOPE: LOCAL — execute within this RPT only. Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18. Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Capture the SELECT query that populates 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' (the INSERT … SELECT or MERGE source). Step 3 [INLINE INTO CONSUMER] Open the SQL procedure called by consumer 'EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18'. Replace the direct table reference to 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' with the extracted query as a WITH (CTE) clause or subquery. Step 4 [VALIDATE] Run 3+ full pipeline cycles. Compare row counts and key metrics against the Step 1 baseline. Step 5 [DECOMMISSION] After parity is confirmed: • Remove Tidal job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' from the Tidal schedule. • Drop table 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' from the database. • Remove all Tidal scheduler dependency edges pointing to this job. [JOB → SQL MAPPING] MV refresh job : EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 [SQL: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC] Consumer job : EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 [SQL: PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA] | STEP 1 — ESTABLISH BASELINE (all 6 RPTs) Before any code change, capture these metrics for EVERY RPT pipeline listed: • Row counts in each consumer job's target table • End-to-end cycle-time per RPT (wall clock) • SLA breach count over the last 5 runs per RPT RPTs to baseline: RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST Store results in a shared comparison spreadsheet for parity sign-off. STEP 2 — EXTRACT MV SOURCE DEFINITION (one-time, reused by all consumers) Open SQL procedure: FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC Find the INSERT … SELECT (or MERGE) that populates 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC'. Copy the core SELECT query and save it as a shared CTE template: WITH FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC AS ( <paste extracted SELECT here> ) This single CTE definition will be added to EVERY consumer job below. STEP 3 — WAVE 1 CODE CHANGES (1 unique SQL procedure(s) to change) Job : EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 SQL : PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA Impacts: 6 RPT(s): RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST Changes required: a) Open PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA and add the CTE from Step 2 at the top. b) Replace every FROM / JOIN reference to 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' with the CTE name. c) This ONE SQL change resolves all 6 RPT pipeline(s) above. d) After parity (Step 4), remove the Tidal dependency edge on 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' in each of the 6 affected RPT Tidal schedule(s). STEP 4 — WAVE 1 VALIDATION (all 6 RPTs) Deploy Wave changes and run 3+ full pipeline cycles for ALL affected RPTs. Confirm across every RPT: • Row counts match the Step 1 baseline (±0). • Key metrics (claim totals, payment amounts) are identical. Do NOT proceed to the next wave until ALL RPTs have signed off on parity. STEP 5 — TIDAL SCHEDULER CLEANUP (repeat for each of the 6 RPT schedules) Once ALL consumer jobs have passed parity in PRODUCTION: For EACH RPT in [RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST]: • Remove Tidal job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' from that RPT's Tidal schedule. • Delete ALL inbound Tidal dependency edges pointing TO 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. • Delete ALL outbound Tidal dependency edges pointing FROM 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. STEP 6 — DATABASE CLEANUP (global, one-time) • EXEC sp_rename 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC', 'DEPRECATED_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' — 30-day safety hold. • After 30 days with no incidents across ALL 6 RPTs: DROP TABLE DEPRECATED_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC • Remove any SQL VIEWs, synonyms, or grants referencing this table.

## RPT Rollout Plan
Execution Wave | ID | Category | Target Table | Scope | Risk | Priority Score | # Affected Jobs | Affected Jobs (List) | Prerequisites
Wave 1 — Low Risk (Local) (1 items)
Wave 1 — Low Risk (Local) | C-4 | C. Near-Duplicate Procedures | rpt_claim_sum_r | LOCAL | LOW | 61 | 2 | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
Wave 2 — Medium Risk (Local) (5 items)
Wave 2 — Medium Risk (Local) | M-1 | M. Orchestration Edge Without Data Handoff (MV->MV) | FCT_GRP_CLAIM_NOTE_R_MV_SSL | LOCAL | MEDIUM | 52 | 2 | EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1 EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
Wave 2 — Medium Risk (Local) | A-1 | A. Redundant Multi-Source Load | RPT_CLAIM_DTL_R | LOCAL | MEDIUM | 47 | 2 | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
Wave 2 — Medium Risk (Local) | A-2 | A. Redundant Multi-Source Load | rpt_claim_sum_r | LOCAL | MEDIUM | 47 | 2 | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
Wave 2 — Medium Risk (Local) | E-3 | E. Dead MV — Zero Consumers (Decommission Candidate) | FCT_GRP_CLAIM_NOTE_R_MV_SSL | LOCAL | MEDIUM | 47 | 1 | EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1 | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
Wave 2 — Medium Risk (Local) | G-1 | G. Duplicate Column-Lineage Paths | rpt_claim_sum_r | LOCAL | MEDIUM | 43 | 2 | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | Row-count parity and cycle-time comparison for 3+ runs within this RPT
Wave 3 — High Risk (Local) (2 items)
Wave 3 — High Risk (Local) | N-1 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_CLAIM_DTL_R | LOCAL | HIGH | 28 | 1 | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
Wave 3 — High Risk (Local) | N-2 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_FCT_RPT_CLAIM_SUMMARY_R | LOCAL | HIGH | 28 | 1 | EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
Global Wave — Cross-RPT Program (3 items)
Global Wave — Cross-RPT Program | O-1 | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | GLOBAL | LOW | 62 | 1 | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | Verify the GTT result set is referenced only once; if referenced multiple times, keep the GTT (CTE re-evaluation risk in Oracle).
Global Wave — Cross-RPT Program | E-1 | E. MV Elimination Candidate | DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL | GLOBAL | HIGH | 55 | 2 | EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2 EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 | Row-count parity, key-metric parity, and 3-cycle runtime comparison Note: EXECUTE_GLOBAL_PROGRAM is set because the MV refresh job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2' appears as a Tidal scheduling dependency in 6 RPT pipeline(s) (RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST). Even though only 1 job(s) consume the MV data, removing the refresh job from Tidal requires updating the dependency edges in ALL those RPT pipelines.
Global Wave — Cross-RPT Program | E-2 | E. MV Elimination Candidate | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC | GLOBAL | HIGH | 54 | 2 | EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18 | Row-count parity, key-metric parity, and 3-cycle runtime comparison Note: EXECUTE_GLOBAL_PROGRAM is set because the MV refresh job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' appears as a Tidal scheduling dependency in 6 RPT pipeline(s) (RPT_CLAIM_DTL_R, RPT_CLAIM_NOTE_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST). Even though only 1 job(s) consume the MV data, removing the refresh job from Tidal requires updating the dependency edges in ALL those RPT pipelines.

## Action Items
Rank | ID | Category | Target Table | Risk | Scope | Priority Score | What To Do | SQL Objects | Est. Saved (min)
1 | O-1 | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | LOW | GLOBAL | 62 | NAMING: No rename needed — '_GTT' is the correct Oracle convention. HOP REDUCTION: 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' stages data between steps within the same procedure. Evaluate replacing with a WITH clause (CTE): (1) If the result is read MORE than once inside the procedure → keep the GTT (Oracle may re-execute a CTE each time it is referenced). (2) If the result is read EXACTLY ONCE → rewrite as a CTE to eliminate the physical write/read cycle. | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS | 0
2 | C-4 | C. Near-Duplicate Procedures | rpt_claim_sum_r | LOW | LOCAL | 61 | [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 0
3 | E-1 | E. MV Elimination Candidate | DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL | HIGH | GLOBAL | 55 | Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3. Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2'. Capture the SELECT query that populates 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' (the INSERT … SELECT or MERGE source). Step 3 [INLINE INTO CONSUMER] Open the SQL procedure called by consumer 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Replace the direct table reference to 'DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL' with the extracted query as a WITH (CTE) clause or subquery. Step 4 [VALIDATE] Run 3+ full pipeline cycles. Compare row counts and key metrics against the Step 1 baseline. Step 5 [DECOMMISSION] After parity is confirmed: [JOB → SQL MAPPING] | DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC | 1.91
4 | E-2 | E. MV Elimination Candidate | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC | HIGH | GLOBAL | 54 | Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18. Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Capture the SELECT query that populates 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' (the INSERT … SELECT or MERGE source). Step 3 [INLINE INTO CONSUMER] Open the SQL procedure called by consumer 'EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18'. Replace the direct table reference to 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' with the extracted query as a WITH (CTE) clause or subquery. Step 4 [VALIDATE] Run 3+ full pipeline cycles. Compare row counts and key metrics against the Step 1 baseline. Step 5 [DECOMMISSION] After parity is confirmed: [JOB → SQL MAPPING] | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.main | 5.46
5 | M-1 | M. Orchestration Edge Without Data Handoff (MV->MV) | FCT_GRP_CLAIM_NOTE_R_MV_SSL | MEDIUM | LOCAL | 52 | Validate edge-level dependency cleanup for 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1' -> 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Checklist: (1) confirm 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' SQL does not reference ['FCT_GRP_CLAIM_NOTE_R_MV_SSL'], (2) verify no hidden side-effects/temp-table dependencies, (3) remove or relax this scheduler edge in Tidal, (4) run parity + cycle-time comparison for 3+ runs. | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC FCT_GRP_CLAIM_NOTE_R_MV_SSL | 22.51
6 | A-1 | A. Redundant Multi-Source Load | RPT_CLAIM_DTL_R | MEDIUM | LOCAL | 47 | [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19, EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS | PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC | 0
7 | A-2 | A. Redundant Multi-Source Load | rpt_claim_sum_r | MEDIUM | LOCAL | 47 | [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 0
8 | E-3 | E. Dead MV — Zero Consumers (Decommission Candidate) | FCT_GRP_CLAIM_NOTE_R_MV_SSL | MEDIUM | LOCAL | 47 | DECOMMISSION CANDIDATE — Action required: (1) Confirm 'FCT_GRP_CLAIM_NOTE_R_MV_SSL' has no consumers by searching all SQL packages and procedures for any SELECT/JOIN referencing 'FCT_GRP_CLAIM_NOTE_R_MV_SSL'. (2) Cross-verify with the script LLM summaries: the table does NOT appear in any summary's INPUT_DEPENDENCIES — supporting the dead-write assessment. (3) If confirmed zero usage, remove the refresh job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1' from the Tidal schedule and drop the MV definition. | FCT_GRP_CLAIM_NOTE_R_MV_SSL | 22.51
9 | G-1 | G. Duplicate Column-Lineage Paths | rpt_claim_sum_r | MEDIUM | LOCAL | 43 | Consolidate column writes - only 1 job needs to load 1 columns from lt_var_upd_tbl_amt_typ, lt_var_upd_tbl_reserveamt_typ, lt_var_upd_tbl_typ3 -> rpt_claim_sum_r. | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 0
10 | N-1 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_CLAIM_DTL_R | HIGH | LOCAL | 28 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_CLAIM_DTL_R' are derived from ['RPT_FCT_RPT_CLAIM_SUMMARY_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' by joining to the underlying DIM/FCT tables that feed RPT_FCT_RPT_CLAIM_SUMMARY_R, rather than reading the pre-aggregated summary. (3) This eliminates the cross-cycle lag — the indicator columns will reflect the CURRENT cycle's source data instead of the previous cycle's summary. (4) Validate: run 3 consecutive daily cycles comparing row counts and indicator column distributions before/after the change. Risk: HIGH — the folded logic must produce equivalent results to avoid silent data drift in downstream reports. | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS | 0
11 | N-2 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_FCT_RPT_CLAIM_SUMMARY_R | HIGH | LOCAL | 28 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_FCT_RPT_CLAIM_SUMMARY_R' are derived from ['RPT_CLAIM_DTL_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24' by joining to the underlying DIM/FCT tables that feed RPT_CLAIM_DTL_R, rather than reading the pre-aggregated summary. (3) This eliminates the cross-cycle lag — the indicator columns will reflect the CURRENT cycle's source data instead of the previous cycle's summary. (4) Validate: run 3 consecutive daily cycles comparing row counts and indicator column distributions before/after the change. Risk: HIGH — the folded logic must produce equivalent results to avoid silent data drift in downstream reports. | PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.main | 0

## Graph Overview
RPT Table | RPT_CLAIM_NOTE_R
Total Nodes | 15
Total Edges | 22
Max Depth | 3
Node Category Breakdown
Category | Count
DIM | 8
FCT | 3
MV | 3
RPT | 1
Depth Breakdown
Depth | Node Count | Categories
0 | 1 | RPT:1
1 | 11 | DIM:6, FCT:3, MV:2
2 | 1 | MV:1
3 | 2 | DIM:2

## Savings Simulation
Parameter | Value | What this means
RPT Table | RPT_CLAIM_NOTE_R | The report pipeline being analysed
Original node count | 15 | Total Tidal jobs in the dependency graph (root + all upstream dependencies)
Original max depth | 3 | Longest chain of dependent jobs (critical path). Determines minimum pipeline latency.
Jobs removed in simulation (top 10 recs) | 3 | Jobs conceptually eliminated based on the top 10 recommendations (parallelise chain, fold pass-through, consolidate loaders, etc.)
New node count (after simulation) | 14 | Remaining jobs if all top 10 recommendations are implemented
New max depth (after simulation) | 1 | Estimated new critical-path length after removals. Only jobs still connected to root are counted.
Depth reduction | 2 | How many sequential hops are removed from the critical path (pipeline latency improvement)
Node reduction | 1 | How many jobs are eliminated entirely (maintenance and scheduling overhead reduction)
Est. runtime saved — top 10 recs (min) | 52.39 | Sum of estimated pipeline time saved based on avg_runtime data for affected jobs
Verified hop savings — top 10 recs | 9 | Total hops with hard lineage/graph evidence that they can be removed (excludes LLM-only estimates)
Jobs removed in simulation (first 15):
EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS
EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS
EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3

## Job_Optimization_Plan
Job | Script / SQL Object | Step # | Category | Target Table | Risk | Verified Hop Savings | Action Summary
EDP_EDW_CV_SHINKA_LOAD_DIM_GRP_CLAIM_DETAIL_R | PKG_GRP_LOAD_DIFW.main | 1 | C. Source System Architectural Split (By Design) | DIM_GRP_CLAIM_DETAIL_R | LOW | 0 | Do not consolidate. Jobs are intentionally separated by source system (CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies.
EDP_EDW_CV_SHINKA_LOAD_DIM_GRP_CLAIM_DIR_R | PKG_GRP_LOAD_DIFW.main | 1 | C. Source System Architectural Split (By Design) | DIM_GRP_CLAIM_DIR_R | LOW | 0 | Do not consolidate. Jobs are intentionally separated by source system (CV, PACS) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies.
EDP_EDW_EIS_SHINKA_LOAD_FCT_GRP_POLICY_R | PKG_GRP_LOAD_DIFW.main | 1 | C. Source System Architectural Split (By Design) | FCT_GRP_POLICY_R | LOW | 0 | Do not consolidate. Jobs are intentionally separated by source system (PACS, SHINKA) so each source can be placed on hold independently without impacting others. Combining them would couple SLA dependencies.
EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS | 1 | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | LOW | 1 | NAMING: No rename needed — '_GTT' is the correct Oracle convention. ¦ HOP REDUCTION: 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' stages data between steps within the same procedure. Evaluate replacing with a WITH clause (CTE): ¦ (1) If the result is read MORE than once inside the procedure → keep the GTT (Oracle may re-execute a CTE each time it is referenced).
| PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC | 2 | A. Redundant Multi-Source Load | RPT_CLAIM_DTL_R | MEDIUM | 1 | Investigate if loads can be consolidated. ¦ [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19, EDP_
| PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS | 3 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_CLAIM_DTL_R | HIGH | 1 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_CLAIM_DTL_R' are derived from ['RPT_FCT_RPT_CLAIM_SUMMARY_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' by joining to the underlying DIM/FCT tables that feed RPT_FCT_
EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 1 | C. Near-Duplicate Procedures | rpt_claim_sum_r | LOW | 1 | Jobs call different variants of the same base package. Evaluate if variants can be unified with a single parameterized package entry point. ¦ [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as paramete
| PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 2 | A. Redundant Multi-Source Load | rpt_claim_sum_r | MEDIUM | 1 | Investigate if loads can be consolidated. ¦ [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS
| PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 3 | G. Duplicate Column-Lineage Paths | rpt_claim_sum_r | MEDIUM | 1 | Consolidate column writes - only 1 job needs to load 1 columns from lt_var_upd_tbl_amt_typ, lt_var_upd_tbl_reserveamt_typ, lt_var_upd_tbl_typ3 -> rpt_claim_sum_r.
EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24 | PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.main | 1 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_FCT_RPT_CLAIM_SUMMARY_R | HIGH | 1 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_FCT_RPT_CLAIM_SUMMARY_R' are derived from ['RPT_CLAIM_DTL_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24' by joining to the underlying DIM/FCT tables that f
EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2 | DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL, FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC | 1 | E. MV Elimination Candidate | DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL | HIGH | 1 | SCOPE: LOCAL — execute within this RPT only. ¦ Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3. ¦ Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_DIM_GRP_CLAIM_POLICY_DETAIL_EMP_MV_SSL-17.2'. Capture the SELECT query that populates 'DIM_GRP_CLAIM_POLICY_DETAI
EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3 | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC, PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.PRC_DEL_EXT_DATA, PKG_GRP_LOAD_RPT_CLAIM_NOTE_R_INC.main | 1 | E. MV Elimination Candidate | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC | HIGH | 1 | SCOPE: LOCAL — execute within this RPT only. ¦ Step 1 [BASELINE] Record row-count and key-metric baseline for consumer job: EDP_GRP_EDW_LOAD_RPT_CLAIM_NOTE_R-18. ¦ Step 2 [EXTRACT MV DEFINITION] Open the SQL procedure called by Tidal job 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Capture the SELECT query that populates 'FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC' (the INSERT … SELEC
EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1 | FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL_INC, FCT_GRP_CLAIM_NOTE_R_MV_SSL | 1 | M. Orchestration Edge Without Data Handoff (MV->MV) | FCT_GRP_CLAIM_NOTE_R_MV_SSL | MEDIUM | 1 | Validate edge-level dependency cleanup for 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_MV_SSL-17.1' -> 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3'. Checklist: (1) confirm 'EDP_GRP_EDW_MV_REFRESH_FCT_GRP_CLAIM_NOTE_R_DRQ_MV_SSL-17.3' SQL does not reference ['FCT_GRP_CLAIM_NOTE_R_MV_SSL'], (2) verify no hidden side-effects/temp-table dependencies, (3) remove or relax this schedule
| FCT_GRP_CLAIM_NOTE_R_MV_SSL | 2 | E. Dead MV — Zero Consumers (Decommission Candidate) | FCT_GRP_CLAIM_NOTE_R_MV_SSL | MEDIUM | 1 | DECOMMISSION CANDIDATE — Action required: ¦ (1) Confirm 'FCT_GRP_CLAIM_NOTE_R_MV_SSL' has no consumers by searching all SQL packages and procedures for any SELECT/JOIN referencing 'FCT_GRP_CLAIM_NOTE_R_MV_SSL'. ¦ (2) Cross-verify with the script LLM summaries: the table does NOT appear in any summary's INPUT_DEPENDENCIES — supporting the dead-write assessment.