## Hop Recommendations
ID | Recommendation Type | Evidence Level | Confidence Scope | Category | Target Table | SQL Objects Called | Description | Affected Jobs | Current Hops | Verified Hop Savings | Runtime Affected (sec) | Estimated Runtime Saved (sec) | Estimated Runtime Saved (min) | LLM Signals | LLM Redundancy Signals | LLM Performance Signals | LLM Logic Signals | Risk | Priority Score | Recommendation | Supporting Evidence | Edge Source Writes | Edge Target Reads | Implementation Decision | Execution Wave | Global RPT Count Impacted | Global Consumer Count | Global Runtime Affected (min) | Global Est Runtime Saved (min) | Blast Radius Score | Prerequisites
O-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS | 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' is an Oracle Global Temporary Table (GTT) — the '_GTT' suffix is the correct Oracle naming convention, so NO rename is needed. Script analysis confirms it is created and consumed within the same stored procedure (intra-procedure staging). GTTs represent a physical staging hop that may be eliminatable. | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 62 | NAMING: No rename needed — '_GTT' is the correct Oracle convention. HOP REDUCTION: 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' stages data between steps within the same procedure. Evaluate replacing with a WITH clause (CTE): (1) If the result is read MORE than once inside the procedure → keep the GTT (Oracle may re-execute a CTE each time it is referenced). (2) If the result is read EXACTLY ONCE → rewrite as a CTE to eliminate the physical write/read cycle. (3) Validate row counts and key metrics before and after the change. |  |  |  | EXECUTE_GLOBAL_PROGRAM | GLOBAL_WAVE_1_PLUS | 5 | 0 | 49.76 | 0 | 5 | Verify the GTT result set is referenced only once; if referenced multiple times, keep the GTT (CTE re-evaluation risk in Oracle).
C-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SAME_PKG_VARIANT | C. Near-Duplicate Procedures | rpt_claim_sum_r | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 2 jobs load 'rpt_claim_sum_r' with >=85% identical target column sets. SQL objects called: ['PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA', 'PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS', 'PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main']. | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | LOW | 61 | Jobs call different variants of the same base package. Evaluate if variants can be unified with a single parameterized package entry point. [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS |  |  |  | EXECUTE_LOCALLY | WAVE_1 | 1 | 1 | 5.38 | 0 | 2 | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
A-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE | DIFF_SQL_OBJECTS | A. Redundant Multi-Source Load | RPT_CLAIM_DTL_R | PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS | Table 'RPT_CLAIM_DTL_R' loaded by 2 jobs: ['EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19', 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS']. SQL: ['PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA', 'PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS'] | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEDIUM | 47 | Investigate if loads can be consolidated. [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19, EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS |  |  |  | EXECUTE_LOCALLY | WAVE_2 | 1 | 1 | 51.05 | 0 | 2 | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
A-2 | HOP_REDUCTION | GRAPH_OR_LINEAGE | SAME_PKG_VARIANT | A. Redundant Multi-Source Load | rpt_claim_sum_r | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | Table 'rpt_claim_sum_r' loaded by 2 jobs: ['EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22', 'EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS']. SQL: ['PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA', 'PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS', 'PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main'] | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEDIUM | 47 | Investigate if loads can be consolidated. [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS |  |  |  | EXECUTE_LOCALLY | WAVE_2 | 1 | 1 | 5.38 | 0 | 2 | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
G-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | G. Duplicate Column-Lineage Paths | rpt_claim_sum_r | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 1 columns flow lt_var_upd_tbl_amt_typ, lt_var_upd_tbl_reserveamt_typ, lt_var_upd_tbl_typ3 -> rpt_claim_sum_r via 2 different jobs (same path). | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MEDIUM | 43 | Consolidate column writes - only 1 job needs to load 1 columns from lt_var_upd_tbl_amt_typ, lt_var_upd_tbl_reserveamt_typ, lt_var_upd_tbl_typ3 -> rpt_claim_sum_r. |  |  |  | EXECUTE_LOCALLY | WAVE_2 | 1 | 1 | 5.38 | 0 | 2 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
N-1 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | N. Circular Update Chain (Post-Load Self-Reference) | RPT_CLAIM_DTL_R | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS | Job 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' is a full-load job for 'RPT_CLAIM_DTL_R', but it also reads ['RPT_FCT_RPT_CLAIM_SUMMARY_R'] — table(s) that are DOWNSTREAM of 'RPT_CLAIM_DTL_R' (i.e., they are derived FROM 'RPT_CLAIM_DTL_R' in a previous pipeline cycle). This creates a lagged-cycle circular dependency: the current-run load uses last-cycle aggregated/derived data to fill in indicator or decision columns, meaning the output of 'RPT_CLAIM_DTL_R' in this cycle will differ from what it would be if fresh data were used. Note: 'RPT_CLAIM_DTL_R' gets updated using RPT_FCT_RPT_CLAIM_SUMMARY_R, which is itself derived from 'RPT_CLAIM_DTL_R' — this is a circular feedback loop across pipeline cycles. | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HIGH | 28 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_CLAIM_DTL_R' are derived from ['RPT_FCT_RPT_CLAIM_SUMMARY_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' by joining to the underlying DIM/FCT tables that feed RPT_FCT_RPT_CLAIM_SUMMARY_R, rather than reading the pre-aggregated summary. (3) This eliminates the cross-cycle lag — the indicator columns will reflect the CURRENT cycle's source data instead of the previous cycle's summary. (4) Validate: run 3 consecutive daily cycles comparing row counts and indicator column distributions before/after the change. Risk: HIGH — the folded logic must produce equivalent results to avoid silent data drift in downstream reports. |  |  |  | EXECUTE_LOCALLY | WAVE_3 | 1 | 0 | 49.76 | 0 | 1 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
N-2 | HOP_REDUCTION | GRAPH_OR_LINEAGE |  | N. Circular Update Chain (Post-Load Self-Reference) | RPT_FCT_RPT_CLAIM_SUMMARY_R | PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.main | Job 'EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24' is a full-load job for 'RPT_FCT_RPT_CLAIM_SUMMARY_R', but it also reads ['RPT_CLAIM_DTL_R'] — table(s) that are DOWNSTREAM of 'RPT_FCT_RPT_CLAIM_SUMMARY_R' (i.e., they are derived FROM 'RPT_FCT_RPT_CLAIM_SUMMARY_R' in a previous pipeline cycle). This creates a lagged-cycle circular dependency: the current-run load uses last-cycle aggregated/derived data to fill in indicator or decision columns, meaning the output of 'RPT_FCT_RPT_CLAIM_SUMMARY_R' in this cycle will differ from what it would be if fresh data were used. Note: 'RPT_FCT_RPT_CLAIM_SUMMARY_R' gets updated using RPT_CLAIM_DTL_R, which is itself derived from 'RPT_FCT_RPT_CLAIM_SUMMARY_R' — this is a circular feedback loop across pipeline cycles. | EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HIGH | 28 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_FCT_RPT_CLAIM_SUMMARY_R' are derived from ['RPT_CLAIM_DTL_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24' by joining to the underlying DIM/FCT tables that feed RPT_CLAIM_DTL_R, rather than reading the pre-aggregated summary. (3) This eliminates the cross-cycle lag — the indicator columns will reflect the CURRENT cycle's source data instead of the previous cycle's summary. (4) Validate: run 3 consecutive daily cycles comparing row counts and indicator column distributions before/after the change. Risk: HIGH — the folded logic must produce equivalent results to avoid silent data drift in downstream reports. |  |  |  | EXECUTE_LOCALLY | WAVE_3 | 1 | 0 | 11.18 | 0 | 1 | Row-count parity and cycle-time comparison for 3+ runs within this RPT

## PLSQL Optimization
ID | Recommendation Type | Evidence Level | Confidence Scope | Category | Target Table | SQL Objects Called | Description | Affected Jobs | Current Hops | Verified Hop Savings | Runtime Affected (sec) | Estimated Runtime Saved (sec) | Estimated Runtime Saved (min) | LLM Signals | LLM Redundancy Signals | LLM Performance Signals | LLM Logic Signals | Risk | Priority Score | Recommendation | Supporting Evidence | Edge Source Writes | Edge Target Reads | Implementation Decision | Execution Wave | Global RPT Count Impacted | Global Consumer Count | Global Runtime Affected (min) | Global Est Runtime Saved (min) | Blast Radius Score | Prerequisites

## Summary
Category | # Recs | Verified Hop Savings | Est. Runtime Saved (min) | Unique Jobs Affected | Risk Level | Implementation Decision
HOP REDUCTION RECOMMENDATIONS (Structural / Verified — 7 total)
A. Redundant Multi-Source Load | 2 | 2 | 0 | 4 | MEDIUM | EXECUTE_LOCALLY
C. Near-Duplicate Procedures | 1 | 1 | 0 | 2 | LOW | EXECUTE_LOCALLY
G. Duplicate Column-Lineage Paths | 1 | 1 | 0 | 2 | MEDIUM | EXECUTE_LOCALLY
N. Circular Update Chain (Post-Load Self-Reference) | 2 | 2 | 0 | 2 | HIGH | EXECUTE_LOCALLY
O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | 1 | 1 | 0 | 1 | LOW | EXECUTE_GLOBAL_PROGRAM
Hop Reduction Subtotal | 7 | 7 | 0 | 5
F. OPTIMIZATION FINDINGS (Require SQL / Code Review — 0 total)
Optimization Subtotal | 0 | 0 | 0 | 0
GRAND TOTAL | 7 | 7 | 0 | 5

## Global Decisions
ID | Category | Target Table | Impacted RPTs | Impacted Jobs | Global Consumer Count | Global Est Runtime Saved (min) | Blast Radius | Execution Wave | Recommendation | Implementation Steps
O-1 | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | RPT_CLAIM_DTL_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST | MV Refresh Job (writes 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT'): EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 SQL: PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS Consumer Jobs — 0 job(s): | 0 | 0 | 5 | GLOBAL_WAVE_1_PLUS | NAMING: No rename needed — '_GTT' is the correct Oracle convention. HOP REDUCTION: 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' stages data between steps within the same procedure. Evaluate replacing with a WITH clause (CTE): (1) If the result is read MORE than once inside the procedure → keep the GTT (Oracle may re-execute a CTE each time it is referenced). (2) If the result is read EXACTLY ONCE → rewrite as a CTE to eliminate the physical write/read cycle. (3) Validate row counts and key metrics before and after the change. | STEP 1 — ESTABLISH BASELINE (all 5 RPTs) Before any code change, capture these metrics for EVERY RPT pipeline listed: • Row counts in each consumer job's target table • End-to-end cycle-time per RPT (wall clock) • SLA breach count over the last 5 runs per RPT RPTs to baseline: RPT_CLAIM_DTL_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST Store results in a shared comparison spreadsheet for parity sign-off. STEP 2 — EXTRACT MV SOURCE DEFINITION (one-time, reused by all consumers) Open SQL procedure: PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DEL_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_WAVIER_LTD_IND_COLS Find the INSERT … SELECT (or MERGE) that populates 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT'. Copy the core SELECT query and save it as a shared CTE template: WITH RPT_CLAIM_DTL_R_CLAIMDEC_GTT AS ( <paste extracted SELECT here> ) This single CTE definition will be added to EVERY consumer job below. STEP 3 — TIDAL SCHEDULER CLEANUP (repeat for each of the 5 RPT schedules) Once ALL consumer jobs have passed parity in PRODUCTION: For EACH RPT in [RPT_CLAIM_DTL_R, RPT_CLAIM_SUM_R, RPT_DICS_CLAIMS_DETAIL_OAC_R, RPT_FCT_RPT_CLAIM_SUMMARY_R, RPT_FCT_RPT_CLAIM_SUMMARY_R_HIST]: • Remove Tidal job 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' from that RPT's Tidal schedule. • Delete ALL inbound Tidal dependency edges pointing TO 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19'. • Delete ALL outbound Tidal dependency edges pointing FROM 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19'. STEP 4 — DATABASE CLEANUP (global, one-time) • EXEC sp_rename 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT', 'DEPRECATED_RPT_CLAIM_DTL_R_CLAIMDEC_GTT' — 30-day safety hold. • After 30 days with no incidents across ALL 5 RPTs: DROP TABLE DEPRECATED_RPT_CLAIM_DTL_R_CLAIMDEC_GTT • Remove any SQL VIEWs, synonyms, or grants referencing this table.

## RPT Rollout Plan
Execution Wave | ID | Category | Target Table | Scope | Risk | Priority Score | # Affected Jobs | Affected Jobs (List) | Prerequisites
Wave 1 — Low Risk (Local) (1 items)
Wave 1 — Low Risk (Local) | C-1 | C. Near-Duplicate Procedures | rpt_claim_sum_r | LOCAL | LOW | 61 | 2 | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
Wave 2 — Medium Risk (Local) (3 items)
Wave 2 — Medium Risk (Local) | A-1 | A. Redundant Multi-Source Load | RPT_CLAIM_DTL_R | LOCAL | MEDIUM | 47 | 2 | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
Wave 2 — Medium Risk (Local) | A-2 | A. Redundant Multi-Source Load | rpt_claim_sum_r | LOCAL | MEDIUM | 47 | 2 | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | Row-count parity, key-metric parity, and cycle-time comparison for 3+ runs
Wave 2 — Medium Risk (Local) | G-1 | G. Duplicate Column-Lineage Paths | rpt_claim_sum_r | LOCAL | MEDIUM | 43 | 2 | EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | Row-count parity and cycle-time comparison for 3+ runs within this RPT
Wave 3 — High Risk (Local) (2 items)
Wave 3 — High Risk (Local) | N-1 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_CLAIM_DTL_R | LOCAL | HIGH | 28 | 1 | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
Wave 3 — High Risk (Local) | N-2 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_FCT_RPT_CLAIM_SUMMARY_R | LOCAL | HIGH | 28 | 1 | EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24 | Row-count parity and cycle-time comparison for 3+ runs within this RPT
Global Wave — Cross-RPT Program (1 items)
Global Wave — Cross-RPT Program | O-1 | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | GLOBAL | LOW | 62 | 1 | EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | Verify the GTT result set is referenced only once; if referenced multiple times, keep the GTT (CTE re-evaluation risk in Oracle).

## Action Items
Rank | ID | Category | Target Table | Risk | Scope | Priority Score | What To Do | SQL Objects | Est. Saved (min)
1 | O-1 | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | LOW | GLOBAL | 62 | NAMING: No rename needed — '_GTT' is the correct Oracle convention. HOP REDUCTION: 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' stages data between steps within the same procedure. Evaluate replacing with a WITH clause (CTE): (1) If the result is read MORE than once inside the procedure → keep the GTT (Oracle may re-execute a CTE each time it is referenced). (2) If the result is read EXACTLY ONCE → rewrite as a CTE to eliminate the physical write/read cycle. | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS | 0
2 | C-1 | C. Near-Duplicate Procedures | rpt_claim_sum_r | LOW | LOCAL | 61 | [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 0
3 | A-1 | A. Redundant Multi-Source Load | RPT_CLAIM_DTL_R | MEDIUM | LOCAL | 47 | [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19, EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS | PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC | 0
4 | A-2 | A. Redundant Multi-Source Load | rpt_claim_sum_r | MEDIUM | LOCAL | 47 | [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 0
5 | G-1 | G. Duplicate Column-Lineage Paths | rpt_claim_sum_r | MEDIUM | LOCAL | 43 | Consolidate column writes - only 1 job needs to load 1 columns from lt_var_upd_tbl_amt_typ, lt_var_upd_tbl_reserveamt_typ, lt_var_upd_tbl_typ3 -> rpt_claim_sum_r. | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 0
6 | N-1 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_CLAIM_DTL_R | HIGH | LOCAL | 28 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_CLAIM_DTL_R' are derived from ['RPT_FCT_RPT_CLAIM_SUMMARY_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' by joining to the underlying DIM/FCT tables that feed RPT_FCT_RPT_CLAIM_SUMMARY_R, rather than reading the pre-aggregated summary. (3) This eliminates the cross-cycle lag — the indicator columns will reflect the CURRENT cycle's source data instead of the previous cycle's summary. (4) Validate: run 3 consecutive daily cycles comparing row counts and indicator column distributions before/after the change. Risk: HIGH — the folded logic must produce equivalent results to avoid silent data drift in downstream reports. | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS | 0
7 | N-2 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_FCT_RPT_CLAIM_SUMMARY_R | HIGH | LOCAL | 28 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_FCT_RPT_CLAIM_SUMMARY_R' are derived from ['RPT_CLAIM_DTL_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24' by joining to the underlying DIM/FCT tables that feed RPT_CLAIM_DTL_R, rather than reading the pre-aggregated summary. (3) This eliminates the cross-cycle lag — the indicator columns will reflect the CURRENT cycle's source data instead of the previous cycle's summary. (4) Validate: run 3 consecutive daily cycles comparing row counts and indicator column distributions before/after the change. Risk: HIGH — the folded logic must produce equivalent results to avoid silent data drift in downstream reports. | PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.PRC_GET_CUR_DATA PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.main | 0

## Graph Overview
RPT Table | RPT_EMPLOYEE_R
Total Nodes | 1
Total Edges | 0
Max Depth | 0
Node Category Breakdown
Category | Count
RPT | 1
Depth Breakdown
Depth | Node Count | Categories
0 | 1 | RPT:1

## Savings Simulation
Parameter | Value | What this means
RPT Table | RPT_EMPLOYEE_R | The report pipeline being analysed
Original node count | 1 | Total Tidal jobs in the dependency graph (root + all upstream dependencies)
Original max depth | 0 | Longest chain of dependent jobs (critical path). Determines minimum pipeline latency.
Jobs removed in simulation (top 10 recs) | 2 | Jobs conceptually eliminated based on the top 10 recommendations (parallelise chain, fold pass-through, consolidate loaders, etc.)
New node count (after simulation) | 1 | Remaining jobs if all top 10 recommendations are implemented
New max depth (after simulation) | 0 | Estimated new critical-path length after removals. Only jobs still connected to root are counted.
Depth reduction | 0 | How many sequential hops are removed from the critical path (pipeline latency improvement)
Node reduction | 0 | How many jobs are eliminated entirely (maintenance and scheduling overhead reduction)
Est. runtime saved — top 10 recs (min) | 0 | Sum of estimated pipeline time saved based on avg_runtime data for affected jobs
Verified hop savings — top 10 recs | 7 | Total hops with hard lineage/graph evidence that they can be removed (excludes LLM-only estimates)
Jobs removed in simulation (first 15):
EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R_UPD_IND_COLS
EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS

## Job_Optimization_Plan
Job | Script / SQL Object | Step # | Category | Target Table | Risk | Verified Hop Savings | Action Summary
EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19 | PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS | 1 | O. GTT Intra-Procedure Staging — Evaluate CTE Replacement | RPT_CLAIM_DTL_R_CLAIMDEC_GTT | LOW | 1 | NAMING: No rename needed — '_GTT' is the correct Oracle convention. ¦ HOP REDUCTION: 'RPT_CLAIM_DTL_R_CLAIMDEC_GTT' stages data between steps within the same procedure. Evaluate replacing with a WITH clause (CTE): ¦ (1) If the result is read MORE than once inside the procedure → keep the GTT (Oracle may re-execute a CTE each time it is referenced).
| PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC | 2 | A. Redundant Multi-Source Load | RPT_CLAIM_DTL_R | MEDIUM | 1 | Investigate if loads can be consolidated. ¦ [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_DTL_R.PRC_UPD_WAVIER_LTD_IND_COLS, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19, EDP_
| PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_INSERT_DUMMY_REC, PKG_GRP_LOAD_RPT_CLAIM_DTL_R_INC.PRC_UPD_DECISION_COLS | 3 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_CLAIM_DTL_R | HIGH | 1 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_CLAIM_DTL_R' are derived from ['RPT_FCT_RPT_CLAIM_SUMMARY_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_CLAIM_DTL_R-19' by joining to the underlying DIM/FCT tables that feed RPT_FCT_
EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22 | PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 1 | C. Near-Duplicate Procedures | rpt_claim_sum_r | LOW | 1 | Jobs call different variants of the same base package. Evaluate if variants can be unified with a single parameterized package entry point. ¦ [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as paramete
| PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 2 | A. Redundant Multi-Source Load | rpt_claim_sum_r | MEDIUM | 1 | Investigate if loads can be consolidated. ¦ [CONCRETE] Jobs call different SQL objects: PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main. Action: Create single parameterized procedure accepting variant/offset/source as parameter. Affected jobs: EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R-22, EDP_GRP_EDW_LOAD_RPT_CLAIM_SUM_R_UPD_COLS
| PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.PRC_UPD_COLS, PKG_GRP_LOAD_RPT_CLAIM_SUM_R.main | 3 | G. Duplicate Column-Lineage Paths | rpt_claim_sum_r | MEDIUM | 1 | Consolidate column writes - only 1 job needs to load 1 columns from lt_var_upd_tbl_amt_typ, lt_var_upd_tbl_reserveamt_typ, lt_var_upd_tbl_typ3 -> rpt_claim_sum_r.
EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24 | PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.PRC_GET_CUR_DATA, PKG_GRP_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R.main | 1 | N. Circular Update Chain (Post-Load Self-Reference) | RPT_FCT_RPT_CLAIM_SUMMARY_R | HIGH | 1 | CIRCULAR DEPENDENCY — Action required: (1) Identify which columns in 'RPT_FCT_RPT_CLAIM_SUMMARY_R' are derived from ['RPT_CLAIM_DTL_R'] (typically indicator/decision columns like V_HAS_LTD_IND_R, decision dates, turnaround buckets). (2) Fold that aggregation logic DIRECTLY into the INSERT SELECT of 'EDP_GRP_EDW_LOAD_RPT_FCT_RPT_CLAIM_SUMMARY_R-24' by joining to the underlying DIM/FCT tables that f